## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
-OdkMmXG0EaLwlFj-WEVVskAGYYn | Highlight project contribution | Final Presentation | Not started | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-04-30 | 2026-05-01 | 2026-05-01 | false | false |  |  |  |  | Purple
1x6dJEdzqUuUeMxH8tnyjMkAFQrv | finalize report formatting | Documentation (Report , README) | Completed | Medium | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-12-26 | 2025-12-31 | 2026-01-04 | false | false | 2026-01-03 | DULSHAN K.M.S it22565730 | 2/2 | Format report;Proofread content | Silver
59x9mHORw0ygs9VLCbt0C8kAF-Bg | Risk mitigation planing | Risk Management & Contingency Planing | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-08-27 | 2025-08-29 | 2025-09-12 | false | false | 2025-09-12 | PRABUDDHINI R P A it22907820 | 2/2 | Define mitigation strategies;Prepare contingency plan | Green
7avZAWbKu0OwTQistWiUXMkAFznM | Individual component selection | Pre Planning & Topic Selection | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-06-11 | 2025-06-12 | 2025-06-26 | false | false | 2025-06-24 | DULSHAN K.M.S it22565730 |  |  | Bronze
88YC1sTHQEqvIk2ZALEN48kAK9Bx | Summarize technical implementation | Progress Presentation 2 | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-08 | 2026-01-10 | 2026-01-31 | false | false | 2026-01-31 | PRABUDDHINI R P A it22907820 | 2/2 | Highlight improvements;Summarize compeletd work | Brown
9v2-SknG9kKHoufuvkA3hskABUeB | Prepare presentation slides | Progress Presentation 2 | Completed | Urgent | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-07 | 2026-01-08 | 2026-01-15 | false | false | 2026-01-15 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Desaign slides;Add visuals(diagrams,charts,screenshots) | Aqua
BDzXb_dVeU-eP2GTMPuuEckAJQ1_ | Backend Development | Implementation | Completed | Urgent | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-15 | 2025-09-16 | 2025-10-23 | false | false | 2025-10-23 | PRABUDDHINI R P A it22907820 | 2/2 | Connect database;Develop APIs | Bronze
CyGt8dx8bkebpcyJcIfvo8kALwVx | Prepare literature review section draft | Literature Review | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-07-02 | 2025-07-02 | 2025-07-30 | false | false | 2025-07-30 | ARIYATHILAKA B.P.D.M.K it22590626 |  |  | Lavender
CyXe2i5yYEeILlPBNuDvJ8kAAEdY | Integrate backend | Prepare Research webiste | Completed | Important | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-03 | 2026-03-03 | 2026-03-24 | false | false | 2026-03-24 | WICKRAMARATHE H.P.R.D.T it22571984 |  |  | Blue
E0Cb5STzB0KufWVkFx6keckAN5R- | Outline & Structure Planning | Research Paper Preparation | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-02 | 2026-01-04 | 2026-01-24 | false | false | 2026-01-24 | PRABUDDHINI R P A it22907820 | 2/2 | Define sections;Create outline | Dark blue
EHqOuewSoU22AjOPbM9owMkAIbK7 | Formatting & Standardization | Prepare Final Report | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-15 | 2026-03-13 | 2026-03-27 | false | false | 2026-03-26 | PRABUDDHINI R P A it22907820 | 2/2 | Ensure consistency (numbering, captions, alignment);Apply formatting guidelines | Light blue
G6SqQGXZ806-5osOaQlLFMkAH4FM | Data collection strategy | Data Collection & Preparation Planing | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-28 | 2025-10-01 | 2025-10-16 | false | false | 2025-10-16 | ARIYATHILAKA B.P.D.M.K it22590626 | 1/1 | Transform dataset | Yellow
HZ0FB4kXgUyuWNtFidcul8kAEnhQ | Topic justification draft | Pre Planning & Topic Selection | Completed | Important | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-06-07 | 2025-06-09 | 2025-06-30 | false | false | 2025-06-30 | ARIYATHILAKA B.P.D.M.K it22590626 | 1/1 | Individual component selection | Purple
I97uuWEldEOSSkLfY56MxskALcup | Add references and citations | Prepare Final Report | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-04 | 2026-03-06 | 2026-03-20 | false | false | 2026-03-20 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Add refernces and citations;Insert diagrams, tablets | Dark green
LHc59h9FDkuk4FP0fdXCIckAAS1r | Add project content | Prepare Research webiste | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-16 | 2026-03-18 | 2026-03-27 | false | false | 2026-03-26 | ARIYATHILAKA B.P.D.M.K it22590626 |  |  | Purple
LgFXIpfGXEGQejlSHhYbkckAKaz0 | Research Existing work | Literature Review | Completed | Important | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-02-27 | 2025-03-01 | 2025-03-21 | false | false | 2025-03-21 | PRABUDDHINI R P A it22907820 | 2/2 | Collect research paper;analyze key approaches | Brown
Ls_XvmjjU0iR2BQkVBN35MkAMWCA | Reheasal | Progress Presentation 1 | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-15 | 2026-01-15 | 2026-01-15 | false | false | 2026-01-15 | PRABUDDHINI R P A it22907820 | 2/2 | Practice presentation;Improve timing | Orange
NLWyARifD0e8W33uIU-WKMkAPsPA | Assign Component ownership and reviews | Topic Finalization & Approval | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-08-01 | 2025-08-01 | 2025-08-10 | false | false | 2025-08-08 | ARIYATHILAKA B.P.D.M.K it22590626
PLSmwIK5H0CfVTTr8P0KxskAMpGZ | Fix the bugs | Testing & Evaluation for PP1 | Completed | Urgent | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-12-23 | 2025-12-23 | 2025-12-30 | false | false | 2025-12-30 | ARIYATHILAKA B.P.D.M.K it22590626 | 1/1 | Fix errors | Peach
PPu6kt925UGcqIRq0CkeLckAJ4o7 | Prepare system demo | Progress Presentation 1 | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-01 | 2026-01-07 | 2026-01-07 | false | false | 2026-01-07 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Prepare system demo;Test demo flow | Marigold
Q9F22XRlCEiRdaRIDPMY2MkAGTIU | Practice presentation delivery | Progress Presentation 2 | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-14 | 2026-01-28 | 2026-01-28 | false | false | 2026-01-28 | PRABUDDHINI R P A it22907820 | 2/2 | Refine slides and speaking points;Practice presentation with time management | Dark gray
QoSfQ2EVLUat6UcOvAb9wckAOR7N | Document requirement specification | Requirement Analysis | Completed | Low | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-08-14 | 2025-08-14 | 2025-08-21 | false | false | 2025-08-20 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | review and finalize;Prepare SRS Document
QwH7-aszV0CJshyunG0h_skANyUe | Risk analysis | Risk Management & Contingency Planing | Completed | Medium | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-08-08 | 2025-08-01 | 2025-08-09 | false | false | 2025-08-09 | DULSHAN K.M.S it22565730 | 2/2 | Evaluate risk impact;Prioritize risks | Light gray
RNZTcFw5pUuv9ZI2tY9GIckAMlCf | UI/UX Design | Design / Architecture | Completed | Low | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-06 | 2025-09-08 | 2025-09-22 | false | false | 2025-09-22 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Create wireframes;Design final UI | Light gray
RtPfAuLnrkiZpK_7SnzCTMkAH21s | Rehearsal & Final Adjusments | Final Presentation | Not started | Important | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-04-30 | 2026-05-01 | 2026-05-05 | false | false |  |  | 2/2 | Practice full presentation with time management;Refine slides, demo flow and speaking clarity | Pink
TLTxsRbG0kiujBSt0ttKiMkAJQ7t | Final topic selection | Topic Finalization & Approval | Completed | Urgent | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-06-25 | 2025-07-01 | 2025-07-07 | false | false | 2025-07-07 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Compare shortlisted topics;Select final topic | Blue
TRVEq7rAsUicw9NsanB5j8kAAz9g | Update project progress | Progress Presentation 2 | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-14 | 2026-01-15 | 2026-01-22 | false | false | 2026-01-22 | PRABUDDHINI R P A it22907820 | 2/2 | test demo flow and avoid errors;Select key feature to demostrate | Purple
Vz03R_qq-kCqnIH3D5UWb8kAPQEL | Final review & submission preparation | Research Paper Preparation | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-25 | 2026-01-31 | 2026-02-09 | false | false | 2026-02-09 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Prepare submission files;Perform plagiarism check & corrections | Yellow
W-Exz3GQukuAkkrrptplt8kALEtK | Plan website structure | Prepare Research webiste | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-14 | 2026-03-10 | 2026-03-24 | false | false | 2026-03-24 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Create sitemap and navigation flow;Define website pages | Teal
YCf5bOPYrEuYJD3D8Ja8ockAFuCl | Editing & Formatting | Research Paper Preparation | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-05 | 2026-01-06 | 2026-01-20 | false | false | 2026-01-20 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Review proofread;Format paper | Gray
ZeLkT_9ywkymLQGncrwWwskAHyZF | System Evaluation | Testing & Evaluation for PP1 | Completed | Low | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-10 | 2026-02-13 | 2026-02-20 | false | false | 2026-02-20 | PRABUDDHINI R P A it22907820 | 2/2 | Prepare test results;Evaluate performance | Aqua
_3vYuHa5fESbY4v87qLvl8kAH4FS | Integrate system components | Implementation | Completed | Important | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-11-15 | 2025-11-18 | 2025-11-22 | false | false | 2025-11-22 | PRABUDDHINI R P A it22907820 | 4/4 | Academic risk predictor;Adaptive learning path generator;stress level predictor;Attendance trend analyser | Red
_Q8siXoS_E-KjiKXrKpEAckAEPnz | Write final discussions and conclution | Prepare Final Report | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-18 | 2026-02-20 | 2026-03-04 | false | false | 2026-03-04 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Write conclusion and future work;complete discussion and analysis sections | Yellow
_UAjTgWup0O6ntB2d-KfDckALhFB | Risk identification | Risk Management & Contingency Planing | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-02 | 2025-09-05 | 2025-09-09 | false | false | 2025-09-09 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | List possible risks;Categorize risks | Blue
_t-roXGrdEya7312z26vcskAMX_h | Final review before submission | Progress Presentation 2 | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-01-15 | 2026-01-22 | 2026-01-22 | false | false | 2026-01-22 | PRABUDDHINI R P A it22907820 |  |  | Light blue
afXHajxco0u21oIAy1fyKMkAPKPm | Select tool & technologies | Design / Architecture | Completed | Low | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-08 | 2025-09-10 | 2025-09-24 | false | false | 2025-09-24 | WICKRAMARATHE H.P.R.D.T it22571984 |  |  | Blue
baTtQnkUPUyht6bAQkJ6-ckAGl2q | Create Final Presentation slides | Final Presentation | In progress | Important | ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-04-30 | 2026-04-30 | 2026-05-01 | false | false |  |  | 2/2 | Apply consistent design;Create slide with visuals
cKEwn_nEkkW5AN9Mm7-6PskABof7 | Identify research gap | Literature Review | Completed | Important | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-07-01 | 2025-07-02 | 2025-07-16 | false | false | 2025-07-16 | DULSHAN K.M.S it22565730 | 2/2 | refine research gap;Compare existing solutions | Plum
cf5hkhr4JkaGcOhrMQbFuMkAAWHF | Data Preprocessing & labelling | Data Collection & Preparation Planing | Completed | Low | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-10-15 | 2025-10-16 | 2025-10-23 | false | false | 2025-10-23 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Handle missing values;remove noise & duplicates | Purple
dvya6Nd00U6LvTVcRTp0DMkAAGmR | Handle error handling and validation | Implementation | Completed | Medium | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-11-10 | 2025-11-14 | 2025-11-28 | false | false | 2025-11-28 | DULSHAN K.M.S it22565730 |  |  | Bronze
iylI1KINCkaSqh2Uowh7mskALNu1 | Compile all report sections | Prepare Final Report | Completed | Urgent | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-09 | 2026-03-06 | 2026-03-20 | false | false | 2026-03-20 | DULSHAN K.M.S it22565730 | 2/2 | organize chapters;Merge all individual sections | Dark gray
jgmOFCqv-U2MyguaBPIAfckALvXP | Integration Testing | Testing & Evaluation for PP1 | Completed | Medium | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-02 | 2026-02-03 | 2026-02-17 | false | false | 2026-02-17 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Resolve integration issues;Test module integrations | Lime
kXI3RR4kWkidPz-aUV6TJ8kAJ0wK | Checked the individual component and fix the bugs | Testing & Evaluation for PP1 | Completed | Important | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-12-16 | 2025-12-17 | 2025-12-31 | false | false | 2025-12-31 | PRABUDDHINI R P A it22907820 | 4/4 | Adaptive learning path generator;Stress level predictor;Academic Risk predictor;Attendance trend analyzer | Red
n5pYEU3X80SdWeps-K1jpMkAHmmi | Select target conference | Research Paper publication | Completed | Important | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-09 | 2026-02-10 | 2026-02-13 | false | false | 2026-02-13 | PRABUDDHINI R P A it22907820 | 2/2 | Check submission guideline;Review conference scope | Yellow
nMXXSzZiK0OSYO-8wCq8oskACyXm | Develop Core module | Implementation | Completed | Low | WICKRAMARATHE H.P.R.D.T it22571984 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-10-27 | 2025-10-28 | 2025-10-30 | false | false | 2025-10-30 | WICKRAMARATHE H.P.R.D.T it22571984 | 2/2 | Implement core logic and model;Optimize performance | Yellow
ozAm8jzhq02oVvxs8lJSAckAHm32 | Check the Repository | Testing & Evaluation for PP1 | Completed | Low | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-12-14 | 2025-12-15 | 2025-12-18 | false | false | 2025-12-18 | DULSHAN K.M.S it22565730 |  |  | Purple
pAdmbxOu7UqTsKsXAGwsk8kAINpi | Define functional requirements | Requirement Analysis | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-08-21 | 2025-08-21 | 2025-08-24 | false | false | 2025-08-24 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | identify user needs;define system functions | Teal
pB6Ptr4RIkCTi2BUldTfv8kAKt3Q | Feasibility & relevance analysis | Pre Planning & Topic Selection | Completed | Medium | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-06-20 | 2025-06-20 | 2025-06-22 | false | false | 2025-06-22 | DULSHAN K.M.S it22565730 | 2/2 | Analyze technical feasibility;Evaluate scope & constrains | Pink
pY1e9rIoVEW7ZVFsFyyY-ckAMVy7 | Supervisor approval & kickoff | Topic Finalization & Approval | Completed | Urgent | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-07-17 | 2025-07-17 | 2025-07-20 | false | false | 2025-07-20 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Prepare proposal summary;get supervisor approval | Lime
phs7hp7yaESQoeOWNESd_8kAE73c | Define non-functional requirements | Requirement Analysis | Completed | Important | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-08-17 | 2025-08-18 | 2025-08-20 | false | false | 2025-08-20 | DULSHAN K.M.S it22565730 | 2/2 | Define performance criteria;Define security constrains | Aqua
qE6rrBGxq0SwVQljXxdDPMkAOoLK | Write README and setup guide | Documentation (Report , README) | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-12-24 | 2025-12-25 | 2025-12-31 | false | false | 2025-12-31 | ARIYATHILAKA B.P.D.M.K it22590626 | 2/2 | Add usage guide;write setup instructions | Orange
r7DQ_5Y1l0KpR9YPaYU7JskAPgnT | Prepare presentation | Progress Presentation 1 | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-28 | 2026-02-28 | 2026-01-03 | false | false | 2026-01-03 | PRABUDDHINI R P A it22907820 | 2/2 | Create presentation slides;Add visuals & diagrams | Lime
s6hSteZ59UaO15ypS8sg4skAEMNJ | Write Paper | Research Paper Preparation | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-01 | 2026-02-01 | 2026-02-04 | false | false | 2026-02-04 | PRABUDDHINI R P A it22907820 | 2/2 | Write Result & Discussion;Write methodology | Teal
se0eHdAx1Eylw7yepeLG_MkAPTp8 | UI/UX Desaign | Prepare Research webiste | Completed | Medium | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-23 | 2026-03-23 | 2026-03-26 | false | false | 2026-03-26 | DULSHAN K.M.S it22565730 | 2/2 | Apply final UI design;Design wireframes | Teal
sxFF0ndM9ECnk_XUGwG-m8kAJZpL | Frontend Developement | Implementation | Completed | Important | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-12-20 | 2025-12-21 | 2025-12-26 | false | false | 2025-12-26 | PRABUDDHINI R P A it22907820 | 1/1 | Built ui component
tFby-sBQQ0CyX9jj-iMzaskAJ4fr | Technical Documentation | Documentation (Report , README) | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-01 | 2026-02-02 | 2026-02-07 | false | false | 2026-02-06 | PRABUDDHINI R P A it22907820 | 2/2 | Document achitecture;Write system descriptions | Dark blue
tH3xLaJJqUilErV2aEWrN8kAFAWv | Data source identification | Data Collection & Preparation Planing | Completed | Low | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-10-20 | 2025-10-20 | 2025-10-24 | false | false | 2025-10-24 | DULSHAN K.M.S it22565730 | 1/1 | collect row data | Brown
uTkiR6WNVUiqQv5_9vN-TskABUSp | Testing & Development | Prepare Research webiste | Completed | Urgent | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-03-28 | 2026-03-28 | 2026-04-01 | false | false | 2026-04-01 | PRABUDDHINI R P A it22907820 | 2/2 | Deploy website;Test Responziveness | Silver
vebwGrMFB0aDiTSYQ-lii8kAGR_B | Prepare submission materials | Research Paper publication | Completed | Medium | ARIYATHILAKA B.P.D.M.K it22590626 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-02-07 | 2026-02-08 | 2026-02-11 | false | false | 2026-02-10 | ARIYATHILAKA B.P.D.M.K it22590626 |  |  | Lime
vuvAYtTuD0G_iwJBseavOMkAH9eY | Team roles & timeline finalization | Topic Finalization & Approval | Completed | Low | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-06-25 | 2025-06-25 | 2025-06-25 | false | false | 2025-06-25 | PRABUDDHINI R P A it22907820 | 0/2 | define time line;Assign team roles | Red
wCyfXBXLx0WjPeQr2UCy08kADjKC | Prepare demo | Final Presentation | Not started | Important | WICKRAMARATHE H.P.R.D.T it22571984;ARIYATHILAKA B.P.D.M.K it22590626;PRABUDDHINI R P A it22907820;DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-04-30 | 2026-05-04 | 2026-05-04 | false | false |  |  | 2/2 | Select key features to showcase;Test demo flow and ensure system stability | Light blue
wxMyn1geikWdRXvvayHkgckAFpl8 | Review & Finalization | Prepare Final Report | In progress | Important | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2026-05-10 | 2026-04-26 | 2026-05-12 | false | false |  |  | 2/2 | Proofread for grammar and technical accuracy;Perform final validation | Lime
xoZCnpxwqUmDeV3m-Kr3ackABUo2 | Database Design | Design / Architecture | Completed | Important | DULSHAN K.M.S it22565730 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-21 | 2025-09-22 | 2025-09-24 | false | false | 2025-09-24 | DULSHAN K.M.S it22565730 | 2/2 | Design ER diagram;Define schema | Plum
yNlNROj6NkWEnpyc2u4OXMkABB96 | Review & finalize design | Design / Architecture | Completed | Medium | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-25 | 2025-09-25 | 2025-09-28 | false | false | 2025-09-28 | PRABUDDHINI R P A it22907820 |  |  | Aqua
ypBqA42F0EWz1Psz334jhckACfqR | Create system architecture diagram | Design / Architecture | Completed | Important | PRABUDDHINI R P A it22907820 | ARIYATHILAKA B.P.D.M.K it22590626 | 2025-09-21 | 2025-09-22 | 2025-09-25 | false | false | 2025-09-23 | PRABUDDHINI R P A it22907820 |  |  | Green

## Plan name
Plan name | AI-POWERED INTELLIGENT EDUCATION SUPPORT SYSTEM
Plan ID | OXXEvP13kUa3oskuc51s5ckAGh2f
Date of export | 04/30/2026